Bachelor's Thesis Timeline

10-Week Plan · Benchmarking Tabular Data Augmentation Techniques for Deep Clustering

Hai Nguyen · B.Sc. Computer Science, LMU Munich

| Topic | Benchmarking Tabular Data Augmentation Techniques for Deep Clustering |
| --- | --- |
| Official processing time | 15 June 2026 – 23 August 2026 (10 weeks) |
| Preparation phase | until 14 June 2026 — before the official start |
| Weekly workload | approx. 20–25 hours (part-time) |
| Estimated total effort | approx. 220 hours (official phase) |
| Submission deadline | Sunday, 23 August 2026 at the latest |
| Prior knowledge | Data Mining course (clustering, NMI/ARI, silhouette); Python tooling and PyTorch are learned during the preparation phase |

# 1  Overview

This plan divides the bachelor's thesis into a preparation phase and five phases across ten official weeks. The central challenge: the topic requires PyTorch and deep learning, while I am starting without experience in numpy, pandas, matplotlib and scikit-learn. Because the official processing time is only ten weeks, all tool onboarding is moved into the preparation phase before 15 June — this keeps the full official period available for the actual research work.

My Data Mining course is a real asset here: clustering methods and the evaluation metrics NMI, ARI and silhouette are already familiar to me. The learning load therefore clearly sits in two areas — the Python tooling and the deep learning part (contrastive learning, PyTorch).

The plan follows three principles: the tools are learned before the official start, a minimal end-to-end pipeline is brought to a working state early (week 4), and writing happens continuously rather than only at the end.

# 2  Preparation phase (until 14 June)

The weeks before the official start on 15 June are firmly reserved for tool onboarding. The goal is to begin on 15 June with a working environment and solid Python skills — so that none of the ten official weeks is spent on pure tool learning.

Tasks

- Set up the Python environment: Miniconda or venv, Jupyter Notebook or VS Code, create a Git repository

- numpy & pandas: arrays and DataFrames, indexing, loading CSV files, simple transformations

- matplotlib: scatter plots, histograms and learning curves

- scikit-learn: StandardScaler, KMeans, plus the metrics NMI, ARI and silhouette

- Mini-project: cluster the Iris or Digits dataset, compute NMI/ARI, plot the embedding in 2D — directly builds on your Data Mining course

- Getting started with PyTorch: tensors and autograd via the tutorial “Deep Learning with PyTorch: A 60 Minute Blitz”

- Skim SCARF (Bahri et al., 2022) once to get a feel for the topic

Result: A working environment, Python fundamentals, and an initial feel for PyTorch and the topic.

# 3  Phase overview

| Phase | Weeks | Period | Focus | Effort |
| --- | --- | --- | --- | --- |
| 0 | – | until 14 Jun | Preparation: tools & environment | lead-in |
| A | 1–2 | 15–28 Jun | Literature review & conception | ≈ 44 h |
| B | 3–5 | 29 Jun–19 Jul | Implementing the benchmark | ≈ 66 h |
| C | 6–7 | 20 Jul–2 Aug | Experiments & sensitivity studies | ≈ 44 h |
| D | 8–9 | 3–16 Aug | Analysis & writing | ≈ 44 h |
| E | 10 | 17–23 Aug | Revision & submission | ≈ 22 h |
|  |  |  | Total effort, official phase (estimate) | ≈ 220 h |

# 4  Detailed weekly plan

PHASE A  ·  LITERATURE REVIEW & CONCEPTION

## Week 1  ·  15–21 Jun 2026

Literature review & consolidating PyTorch

Tasks

- Read SCARF (Bahri et al., 2022) thoroughly — the central methodological reference for feature corruption and contrastive learning on tabular data

- Skim the augmentation survey (Wang et al., 2025), focusing on the sections on tabular data

- Review 3–4 further sources: self-supervised/contrastive learning for tabular data (e.g. VIME, SubTab), deep clustering fundamentals (DEC/IDEC), the SimCLR principle

- Structure the literature notes and maintain bib-refs.bib (BibTeX)

- Consolidate PyTorch: nn.Module, Dataset/DataLoader, training loop and optimizer — building on the preparation phase

- Exercise: train a simple MLP (autoencoder or classifier) on a tabular dataset

Tools & learning focus: PyTorch (full training pipeline), reference management with BibTeX.

Result: Solid PyTorch skills and a well-founded literature overview.   ◆ Milestone M1

## Week 2  ·  22–28 Jun 2026

Fixing the method & drafting Related Work

Tasks

- Fix the methodology: contrastive pretraining of an MLP encoder followed by k-means on the embeddings as the deep clustering backbone

- Select datasets: 3–4 tabular datasets with ground-truth labels (OpenML/UCI), varying in size and dimensionality

- Define the thesis structure; write a rough draft of the “Related Work” chapter

- Supervisor meeting: agree on method, datasets and scope

Tools & learning focus: LaTeX (cleanthesis template), literature work.

Result: Method and datasets fixed, related-work draft, scope confirmed with the supervisor.   ◆ Milestone M2

PHASE B  ·  IMPLEMENTING THE BENCHMARK

## Week 3  ·  29 Jun–5 Jul 2026

Data pipeline & encoder

Tasks

- Data module: loading, preprocessing (scaling numerical and encoding categorical features), train/test split

- Augmentation module as a scaffold with the first technique: feature masking / corruption in the SCARF style

- Implement the encoder network (MLP) that outputs embeddings

Tools & learning focus: PyTorch, pandas.

Result: Data is loaded and augmented correctly; the encoder produces embeddings.

## Week 4  ·  6–12 Jul 2026

Contrastive training & first end-to-end pipeline

Tasks

- Implement the contrastive loss (NT-Xent / InfoNCE)

- Assemble the training loop and connect it to the encoder

- First full run: one dataset, one augmentation → embedding → k-means → NMI/ARI

- Debugging and sanity checks: does the loss decrease, are the embeddings meaningfully separated?

Tools & learning focus: PyTorch.

Result: A minimal working pipeline (MVP) produces first clustering results.   ◆ Milestone M3

## Week 5  ·  13–19 Jul 2026

Completing the benchmark

Tasks

- Add further augmentations: Gaussian noise, feature swapping/shuffling, optionally zeroing or mixup

- Ensure reproducibility: fixed seeds, configuration files, log results as CSV

- Extend the code to all selected datasets and clean it up

- Plan buffer time for debugging

Tools & learning focus: PyTorch, Git.

Result: A complete, reproducible benchmark codebase.

PHASE C  ·  EXPERIMENTS & SENSITIVITY STUDIES

## Week 6  ·  20–26 Jul 2026

Main experiments

Tasks

- Run the full experiments: all augmentations × all datasets, several seeds each

- Use Google Colab for GPU acceleration if needed

- Store results systematically and traceably

Tools & learning focus: PyTorch, Google Colab.

Result: Raw results for all main configurations are available.

## Week 7  ·  27 Jul–2 Aug 2026

Sensitivity studies & failure cases

Tasks

- Hyperparameter and sensitivity studies: masking rate, augmentation strength, embedding dimension

- Investigate limitations and failure cases of the augmentation techniques

- Prepare results as tables and figures

- Supervisor meeting: discuss the results

Tools & learning focus: PyTorch, matplotlib.

Result: Complete experimental results incl. plots and tables.   ◆ Milestone M4

PHASE D  ·  ANALYSIS & WRITING

## Week 8  ·  3–9 Aug 2026

Analysis & core chapters

Tasks

- Analyse the results: which augmentation improves or worsens clustering — and possible explanations

- Write the “Methodology” chapter (LaTeX)

- Write the “Experiments & Results” chapter

Tools & learning focus: LaTeX, matplotlib.

Result: Analysis completed; methodology and results chapters drafted.

## Week 9  ·  10–16 Aug 2026

Discussion & complete first draft

Tasks

- Write the “Discussion” chapter: interpretation, contextualisation, limitations

- Write the introduction, related work (finalise), conclusion & outlook, and abstract

- Merge the full document and hand it to the supervisor

Tools & learning focus: LaTeX.

Result: Complete first draft handed to the supervisor.   ◆ Milestone M5

PHASE E  ·  REVISION & SUBMISSION

## Week 10  ·  17–23 Aug 2026

Revision & submission

Tasks

- Incorporate supervisor feedback

- Proofread: language, consistency, narrative flow

- LaTeX polishing: formatting, references with biber, lists/indexes, figure quality

- Declaration of authorship, final checks, submission format

- Buffer for unforeseen issues

Tools & learning focus: LaTeX.

Result: Submission of the bachelor's thesis — Sunday, 23 Aug 2026 at the latest.   ◆ Milestone M6

# 5  Milestones

Six milestones make progress verifiable. If a milestone is clearly missed, that is a strong signal to talk to the supervisor about adjusting the scope.

|  | When | Date | Outcome |
| --- | --- | --- | --- |
| M1 | End of week 1 | 21 Jun 2026 | PyTorch fundamentals consolidated; well-founded literature overview |
| M2 | End of week 2 | 28 Jun 2026 | Method and datasets fixed; related-work draft; scope agreed with the supervisor |
| M3 | End of week 4 | 12 Jul 2026 | Minimal end-to-end pipeline (MVP) produces first clustering results |
| M4 | End of week 7 | 2 Aug 2026 | Complete experimental results incl. sensitivity studies, tables and figures |
| M5 | End of week 9 | 16 Aug 2026 | Complete first draft handed to the supervisor |
| M6 | End of week 10 | 23 Aug 2026 | Submission of the bachelor's thesis (latest date) |