## Overview
Bachelor's Thesis Timeline — 10-Week Tracker
Benchmarking Tabular Data Augmentation Techniques for Deep Clustering
Official processing time |  | 16 June 2026 – 25 August 2026 (10 weeks)
Preparation phase |  | until 15 June 2026 (before the official start)
Weekly workload |  | approx. 20–25 hours (part-time)
Total effort (planned) |  | approx. 220 hours (official phase)
Submission deadline |  | Monday, 25 August 2026 at the latest
Overall progress |  | 7.692%
Gantt overview
Phase | Focus | Prep until 14 Jun | W1 15 Jun | W2 22 Jun | W3 29 Jun | W4 6 Jul | W5 13 Jul | W6 20 Jul | W7 27 Jul | W8 3 Aug | W9 10 Aug | W10 17 Aug
0 | Preparation: tools & environment
A | Literature review & conception
B | Implementing the benchmark
C | Experiments & sensitivity studies
D | Analysis & writing
E | Revision & submission
◆ | Milestones |  | M1 | M2 |  | M3 |  |  | M4 |  | M5 | M6
How to use: set tasks in the “Checklist” sheet to “Yes” — the overall progress above and the “Tasks done” column in the “Weekly Plan” sheet update automatically.

## Weekly Plan
Weekly Plan
Week | Period | Phase | Focus | Planned hrs | Tasks done | Status | Milestone
Preparation | until 14 Jun | 0 | Set up and practise tools & environment |  | 3 / 7 | Done
Week 1 | 15–22 Jun | A | Literature review & consolidating PyTorch | 22 | 1 / 6 | In progress | M1
Week 2 | 22–29 Jun | A | Fixing the method & drafting Related Work | 22 | 0 / 5 | Open | M2
Week 3 | 29 Jun–5 Jul | B | Data pipeline & encoder | 22 | 0 / 4 | Open
Week 4 | 6–13 Jul | B | Contrastive training & first end-to-end pipeline | 22 | 0 / 4 | Open | M3
Week 5 | 13–19 Jul | B | Completing the benchmark | 22 | 0 / 6 | Open
Week 6 | 20–26 Jul | C | Main experiments | 22 | 0 / 3 | Open
Week 7 | 27 Jul–3 Aug | C | Sensitivity studies & failure cases | 22 | 0 / 5 | Open | M4
Week 8 | 3–9 Aug | D | Analysis & core chapters | 22 | 0 / 4 | Open
Week 9 | 10–17 Aug | D | Discussion & complete first draft | 22 | 0 / 3 | Open | M5
Week 10 | 17–25 Aug | E | Revision & submission | 22 | 0 / 5 | Open | M6
|  |  | Total | 220

## Checklist
Checklist — all tasks
Week | Phase | Task | Done
0 | 0 | Set up the Python environment (Miniconda/venv, Jupyter/VS Code, Git) | Yes
0 | 0 | Learn numpy & pandas: arrays, DataFrames, indexing, loading CSV | Yes
0 | 0 | Learn matplotlib: scatter plots, histograms, learning curves | Yes
0 | 0 | Learn scikit-learn: StandardScaler, KMeans, NMI/ARI/silhouette | No
0 | 0 | Mini-project: cluster Iris/Digits, compute NMI/ARI, plot embedding | No
0 | 0 | Get started with PyTorch: tensors & autograd (60-Minute Blitz) | No
0 | 0 | Skim SCARF (Bahri et al., 2022) once | No
1 | A | Read SCARF (Bahri et al., 2022) thoroughly | Yes
1 | A | Skim the augmentation survey (Wang et al., 2025) | No
1 | A | Review 3–4 further sources (VIME, SubTab, DEC/IDEC, SimCLR) | No
1 | A | Structure literature notes, maintain bib-refs.bib | No
1 | A | Consolidate PyTorch: nn.Module, Dataset/DataLoader, training loop | No
1 | A | Exercise: train a simple MLP on a tabular dataset | No
2 | A | Fix the methodology: contrastive pretraining (MLP encoder) + k-means | No
2 | A | Select 3–4 tabular datasets with ground-truth labels | No
2 | A | Classify each dataset by feature type: fraction of categorical vs. numerical features; identify features with highest mutual information with cluster labels | No
2 | A | Define the structure; write the related-work draft | No
2 | A | Supervisor meeting: agree on method, datasets and scope | No
3 | B | Data module: loading, preprocessing, train/test split | No
3 | B | Augmentation module scaffold: feature masking/corruption (SCARF) | No
3 | B | Implement feature-type mask: categorical → marginal-distribution replacement; numerical → Gaussian noise or scaling | No
3 | B | Implement the encoder network (MLP) | No
4 | B | Implement the contrastive loss (NT-Xent / InfoNCE) | No
4 | B | Assemble the training loop | No
4 | B | First end-to-end run: 1 dataset, 1 augmentation | No
4 | B | Debugging & sanity checks (loss, embedding quality) | No
5 | B | Further augmentations: Gaussian noise, feature swapping, zeroing/mixup | No
5 | B | Add no-augmentation baseline: identity augmentation (each row passed twice unchanged); label "Identity" in all result tables | No
5 | B | Add feature-type-aware pipeline as a fourth technique; label "Type-Aware" in all result tables | No
5 | B | Reproducibility: seeds, configuration files, CSV logging | No
5 | B | Extend the code to all datasets and clean it up | No
5 | B | Buffer time for debugging | No
6 | C | Full experiments: all augmentations × datasets × seeds | No
6 | C | Use Google Colab for GPU acceleration | No
6 | C | Store results systematically | No
7 | C | Sensitivity studies: masking rate, augmentation strength, embedding dim. | No
7 | C | Investigate limitations and failure cases | No
7 | C | Produce stratified results tables: NMI and ARI broken down by dataset taxonomy (>50% categorical vs. mostly numerical) | No
7 | C | Prepare results as tables and figures | No
7 | C | Supervisor meeting: discuss the results | No
8 | D | Analyse results: which augmentation helps/hurts and why | No
8 | D | Analyse stratified results: Identity baseline vs. augmented variants on high-categorical datasets; Type-Aware pipeline improvement | No
8 | D | Write the "Methodology" chapter (LaTeX) | No
8 | D | Write the "Experiments & Results" chapter | No
9 | D | Write the "Discussion" chapter: interpretation, contextualisation, limitations | No
9 | D | Write introduction, related work (finalise), conclusion & outlook, abstract | No
9 | D | Merge the full document, hand it to the supervisor | No
10 | E | Incorporate supervisor feedback | No
10 | E | Proofread: language, consistency, narrative flow | No
10 | E | LaTeX polishing: formatting, references (biber), lists/indexes | No
10 | E | Declaration of authorship & final checks | No
10 | E | Buffer for unforeseen issues | No

## Week1
Task | Status | Until Sunday 22.06
Learn Pytorch
Skim survey